## Web Content Retainer & Starters
| Quarter 1 |  |  | Quarter 2 |  |  | Quarter 3 |  |  | Quarter 4
| Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | 12-Month Investment to TSL | Monthly Investment to TSL
Web Content Retainer | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 48000
Weekly Customer & TSL Project Manager Checkpoint | Quarter 1 Month 1: 4
Bi-weekly Customer & TSL Project Manager Checkpoint |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Quarterly Customer, TSL Project Manager, TSL SME Checkpoint (Discuss content offers/planning for upcoming quarter) | bar: Quarter 1 Month 3; Quarter 2 Month 6; Quarter 3 Month 9; Quarter 4 Month 12
Monthly Internal TSL & SME Checkpoint | bar: Quarter 1 Month 1 to Quarter 4 Month 12
Kickoff Meetings (Goals, Branding, Offers) | Quarter 1 Month 1: 2
Website Style Board with branding information and assets, to inform all future production | bar: Quarter 1 Month 1
Technical Audit of Website by developer (include site speed related to server performance, establish requirements for us working on the site) | bar: Quarter 1 Month 1
Content Audit, Recommendations and Plan, to inform Website Pages, Content Offer Page Intake Call, Blog topics (SEO team to be involved even if no SEO investment) | bar: Quarter 1 Month 1 to Quarter 1 Month 2
Website Pages (6 total, based on templates created under Starter Bundle) | Quarter 2 Month 4: 2; Quarter 3 Month 7: 2; Quarter 4 Month 10: 2
Offer Landing Pages (3 total, based on template created under Starter Bundle) | bar: Quarter 2 Month 4; Quarter 3 Month 7; Quarter 4 Month 10
Blog Articles (12 total) | Quarter 1 Month 2: 3; Quarter 2 Month 4: 3; Quarter 3 Month 7: 3; Quarter 4 Month 10: 3
Web UX Consulting | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 6000
Website audit for User Experience (UX) and Conversion Rate Optimization (CRO) best practices, and report with assessment and recommendations to improve. | bar: Quarter 1 Month 1 to Quarter 1 Month 2
Monthly SME involvement to inform content plans and website updates. Production/implementation of some site optimization recommendations (ex. CTA creation, edits) are also included in this budget. | bar: Quarter 1 Month 3 to Quarter 4 Month 12
Web Content Starter | Quarter 1 Month 1: 11000 | 11000
Website Pages (2 total) | Quarter 1 Month 3: 2
Offer Landing Page (1 total) | bar: Quarter 1 Month 2
Web Content Starter with Homepage Refresh | Quarter 1 Month 1: 18000 | 18000
Homepage Refresh | bar: Quarter 1 Month 2
Website Pages (2 total) | Quarter 1 Month 3: 2
Offer Landing Page (1 total) | bar: Quarter 1 Month 2
Possible Service Combinations
Web Content Starter + Web Content Retainer | 15000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 59000 | 4916.6667
Web Content Starter + Web Content Retainer + Web UX Consulting | 15500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 65000 | 5416.6667
Web Content Starter with Homepage Refresh + Web Content Retainer | 22000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 66000 | 5500
Web Content Starter with Homepage Refresh + Web Content Retainer + Web UX Consulting | 22500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 72000 | 6000